## Forecast by HS Zip
Monday ,July 4 |  | 10 AM Forecast |  |  | 12 Noon Forecast |  |  | 2 PM Forecast |  |  | 4 PM Forecast
HIGH SCHOOL | ZIP | TEMP | HEAT INDEX | HUMIDITY | TEMP | HEAT INDEX | HUMIDITY | TEMP | HEAT INDEX | HUMIDITY | TEMP | HEAT INDEX | HUMIDITY
UNIVERSITY CITY | 92122
KEARNY | 92111
MIRA MESA | 92126
SCRIPPS RANCH | 92131
PATRICK HENRY | 92120
CANYON HILLS | 92124
CRAWFORD | 92115
ED CENTER | 92103
MORSE | 92114
CLAIREMONT | 92117
MADISON | 92117
SAN DIEGO | 92101
LINCOLN | 92113
MISSION BAY | 92109
LA JOLLA | 92037
POINT LOMA | 92106
Tuesday,July 5 |  | 10 AM Forecast |  |  | NOON Forecast |  |  | 2 PM Forecast |  |  | 4 PM Forecast
HIGH SCHOOL | ZIP | TEMP | HEAT INDEX | HUMIDITY | TEMP | HEAT INDEX | HUMIDITY | TEMP | HEAT INDEX | HUMIDITY | TEMP | HEAT INDEX | HUMIDITY
UNIVERSITY CITY | 92122
KEARNY | 92111
MIRA MESA | 92126
SCRIPPS RANCH | 92131
PATRICK HENRY | 92120
CANYON HILLS | 92124
CRAWFORD | 92115
ED CENTER | 92103
MORSE | 92114
CLAIREMONT | 92117
MADISON | 92117
SAN DIEGO | 92101
LINCOLN | 92113
MISSION BAY | 92109
LA JOLLA | 92037
POINT LOMA | 92106
Wednesday,July 6 |  | 10 AM Forecast |  |  | NOON Forecast |  |  | 2 PM Forecast |  |  | 4 PM Forecast
HIGH SCHOOL | ZIP | TEMP | HEAT INDEX | HUMIDITY | TEMP | HEAT INDEX | HUMIDITY | TEMP | HEAT INDEX | HUMIDITY | TEMP | HEAT INDEX | HUMIDITY
UNIVERSITY CITY | 92122
KEARNY | 92111
MIRA MESA | 92126
SCRIPPS RANCH | 92131
PATRICK HENRY | 92120
CANYON HILLS | 92124
CRAWFORD | 92115
ED CENTER | 92103
MORSE | 92114
CLAIREMONT | 92117
MADISON | 92117
SAN DIEGO | 92101
LINCOLN | 92113
MISSION BAY | 92109
LA JOLLA | 92037
POINT LOMA | 92106
Thursday, July 7 |  | 10 AM Forecast |  |  | NOON Forecast |  |  | 2 PM Forecast |  |  | 4 PM Forecast
HIGH SCHOOL | ZIP | TEMP | HEAT INDEX | HUMIDITY | TEMP | HEAT INDEX | HUMIDITY | TEMP | HEAT INDEX | HUMIDITY | TEMP | HEAT INDEX | HUMIDITY
UNIVERSITY CITY | 92122
KEARNY | 92111
MIRA MESA | 92126
SCRIPPS RANCH | 92131
PATRICK HENRY | 92120
CANYON HILLS | 92124
CRAWFORD | 92115
ED CENTER | 92103
MORSE | 92114
CLAIREMONT | 92117
MADISON | 92117
SAN DIEGO | 92101
LINCOLN | 92113
MISSION BAY | 92109
LA JOLLA | 92037
POINT LOMA | 92106
Friday, July 8 |  | 10 AM Forecast |  |  | NOON Forecast |  |  | 2 PM Forecast |  |  | 4 PM Forecast
HIGH SCHOOL | ZIP | TEMP | HEAT INDEX | HUMIDITY | TEMP | HEAT INDEX | HUMIDITY | TEMP | HEAT INDEX | HUMIDITY | TEMP | HEAT INDEX
UNIVERSITY CITY | 92122
KEARNY | 92111
MIRA MESA | 92126
SCRIPPS RANCH | 92131 |  |  |  | 80 | 81 | 53% | 80 | 81 | 52% | 81 | 81 | 50
PATRICK HENRY | 92120 | [6 empty] | 80 | 81 | 53% | 80 | 81 | 51
CANYON HILLS | 92124 |  |  |  | 80 | 81 | 55% | 80 | 81 | 53% | 80 | 81 | 52
CRAWFORD | 92115
ED CENTER | 92103
MORSE | 92114
CLAIREMONT | 92117
MADISON | 92117
SAN DIEGO | 92101
LINCOLN | 92113
MISSION BAY | 92109
LA JOLLA | 92037
POINT LOMA | 92106

## Classroom Air Conditioning Rpt
Classroom Air Conditioning Report
Facilities Planning and Construction
4860 Ruffner St., San Diego, CA 92111
AC SUMMARY REPORT PER DIVISION CODE …07/20/18
|  |  | DIVISION CODE | CLASSROOM COUNT | CLASSROOM W/ AC | % CLASSROOMS WITH AC
|  |  | CDC (CHILD DEV. CENTER) | 46 | 41 | 89.13%
|  |  | ELEM (ELEMENTARY) | 3492 | 2618 | 74.97%
|  |  | MIDD (MIDDLE/JUNIOR) | 1078 | 665 | 61.69%
|  |  | HIGH (SENIOR HIGH) | 1429 | 1056 | 73.9%
|  |  | ATYP/ALTR(ATYPICAL/ALTERNATIVE) | 394 | 339 | 86.04%
|  |  | ADMN (ADMINISTRATIVE) | 0 | 0 | 0%
|  |  | CHTR (CHARTER) | 421 | 322 | 76.48%
|  |  | OCP (OCILE PROGRAM) | 7 | 7 | 100%
|  |  |  | 6867 | 5048 | 73.51%
AC SUMMARY REPORT PER CLIMATE ZONE …07/20/18
|  |  | CLIMATE ZONE | CLASSROOM COUNT | CLASSROOM W/ AC | % CLASSROOMS WITH AC
|  |  | 1 | 811 | 226 | 27.87%
|  |  | 2 | 2914 | 1751 | 60.09%
|  |  | 3 | 3142 | 3071 | 97.74%
|  |  |  | 6867 | 5048 | 73.51%
[9 empty] | NOTES FOR REFERENCES ONLY…. |  |  |  | !!! HIGH PRIORITY/last update
Site Code | Dept Code | Div Code | School | Climate Zone | Update Date | CRs | CRs w/AC | % CRs w/AC | PROJ NAME | ASSIGNED TO | DETAIL INFORMATION | COMMENT
3 | 3 | ELEM | ADAMS ES | 2 | 2018-07-13 | 20 | 20 | 100% | WSM | Dana Peterson | Completed | Completed
4 | 4 | ELEM | ALCOTT ES | 2 | 2018-07-12 | 25 | 0 | 0% | HVAC-P2 | David Beltran | Const 5/19/17 - 11/30/18 | Const in progress
7 | 7 | ELEM | ANGIER ES | 2 | 2018-07-13 | 27 | 27 | 100% | HVAC-ESS | Radik Musin | Completed | Completed
9 | 9 | ELEM | AUDUBON ES | 3 | 2018-07-13 | 38 | 38 | 100% | HVAC 2000 | Michael Appanaitis | Completed | Completed
11 | 11 | ELEM | BAKER ES | 2 | 2018-07-13 | 35 | 5 | 14.29% | HVAC-P2 | Michael Appanaitis | Const 10/17/17 - 12/6/18 | Const in progress
13 | 13 | ELEM | BALBOA ES | 2 | 2018-07-13 | 34 | 3 | 8.824% | WSM | Gabriela Soriano | Const 3/14/18 - 8/7/20 | Const in progress
23 | 17 | ELEM | BARNARD ES @ BAYVIEW TERRACE | 1 | 2018-07-13 | 27 | 27 | 100% | HVAC 200/P2 | David Beltran | Const 7/31/17 - 8/24/18 | Completed
21 | 21 | ELEM | BAY PARK ES | 1 | 2018-07-13 | 25 | 1 | 4% | HVAC-P2 | Joel Early | Const 11/7/17 - 1/9/19 | Const in progress
29 | 29 | ELEM | BIRD ROCK ES | 1 | 2018-07-12 | 22 | 0 | 0% | HVAC-P2 | Kenneth Shroyer | Const 8/22/17 - 7/25/19 | Const in progress
31 | 31 | ELEM | BIRNEY ES | 2 | 2018-07-13 | 27 | 27 | 100% | HVAC-P2 | Richard Kessler | Completed | Completed
33 | 33 | ELEM | BOONE ES | 3 | 2018-07-13 | 36 | 36 | 100% | HVAC 2000 / ESS | Michael Appanaitis | Completed | Completed
39 | 39 | ELEM | BURBANK ES | 2 | 2018-07-13 | 24 | 24 | 100% | HVAC-P2 | Michael Appanaitis | Completed | Completed
41 | 41 | ELEM | CABRILLO ES | 1 | 2017-04-14 | 16 | 0 | 0% | HVAC-P2 | Richard Kessler | Const 10/20/17 - 1/9/19 | Const in progress
43 | 43 | ELEM | CADMAN ES | 2 | 2018-07-12 | 18 | 0 | 0% | HVAC-P2 | David Beltran | Const 8/16/17 - 10/11/19 | Const in progress
55 | 55 | ELEM | CARSON ES | 2 | 2018-07-13 | 34 | 1 | 2.941% | WSM | Lisa Barnes | Const 10/15/19 - 10/15/20 | Waiting const start date
57 | 57 | ELEM | CARVER ES | 3 | 2018-07-12 | 33 | 32 | 96.97% | HVAC 2000 / ESS | Richard Kessler | 1 CR used as storage | Completed
59 | 59 | ELEM | CENTRAL ES | 3 | 2018-07-13 | 51 | 51 | 100% | n/a | n/a | Completed | Completed
60 | 60 | ELEM | CHAVEZ ES | 2 | 2018-07-13 | 35 | 1 | 2.857% | HVAC-P2 | Michael Appanaitis | Const 5/10/19 - 10/8/20 | Waiting const start date
61 | 61 | ELEM | CHESTERTON ES | 2 | 2018-07-13 | 28 | 28 | 100% | HVAC-P2 | Joel Early | Completed | Completed
62 | 62 | ELEM | CHEROKEE POINT ES | 2 | 2018-07-13 | 32 | 32 | 100% | n/a | n/a | Completed | Completed
63 | 63 | ELEM | CHOLLAS/MEAD ES | 3 | 2018-07-13 | 50 | 50 | 100% | n/a | n/a | Completed | Completed
65 | 65 | ELEM | CLAY ES | 3 | 2018-07-13 | 22 | 22 | 100% | n/a | n/a | Completed | Completed
73 | 73 | ELEM | CROWN POINT ES | 1 | 2018-07-13 | 19 | 1 | 5.263% | HVAC-P2 | Joel Early | Const 8/30/17 - 10/12/18 | Const in progress
153 | 74 | CHTR | IFTIN CHARTER @ JACKSON ES | 3 | 2018-07-13 | 22 | 22 | 100% | HVAC 2000 | Kenneth Shroyer | Completed | Completed
75 | 75 | ELEM | CUBBERLEY ES | 2 | 2018-07-13 | 11 | 11 | 100% | HVAC-P2 | Joel Early | Const 9/17 - 7/18 | Completed
77 | 77 | ELEM | CURIE ES | 2 | 2018-07-13 | 30 | 30 | 100% | HVAC 2000 | Kenneth Shroyer | Completed | Completed
78 | 78 | ELEM | DAILARD ES | 3 | 2018-07-13 | 24 | 24 | 100% | n/a | n/a | Completed | Completed
79 | 79 | CHTR | DARNALL CHARTER | 3 | 2018-07-13 | 28 | 28 | 100% | HVAC 2000 | Richard Kessler | Completed | Completed
80 | 80 | MIDD | DANA MS | 1 | 2017-04-14 | 44 | 0 | 0% | HVAC-P2 | Richard Kessler | Const 1/24/18 - 11/28/18 | Const in progress
85 | 85 | ELEM | DEWEY ES | 1 | 2017-04-14 | 24 | 0 | 0% | HVAC-P2 | Rich Kessler | Const 12/12/17 - 8/3/18 | Const in progress
86 | 86 | ELEM | DINGEMAN ES | 3 | 2018-07-13 | 41 | 41 | 100% | HVAC 2000 | Kenneth Shroyer | Completed | Completed
87 | 87 | ELEM | DOYLE ES | 2 | 2018-07-13 | 37 | 37 | 100% | HVAC 2000 | Kenneth Shroyer | Completed | Completed
89 | 89 | ELEM | EDISON ES | 2 | 2018-07-13 | 37 | 37 | 100% | HVAC-P2 | Rich Kessler | Const 5/2/17 - 6/27/18 | Completed
308 | 90 | ELEM | EB SCRIPPS ES | 3 | 2018-07-13 | 42 | 42 | 100% | n/a | n/a | Completed | Completed
15 | 91 | ELEM | EMERSON/BANDINI @ BANDINI | 2 | 2018-07-13 | 19 | 0 | 0% | WSM | Jerry Bott | Const 8/24/18 - 5/1/19 | Design Phase
91 | 91 | ELEM | EMERSON/BANDINI @ EMERSON | 2 | 2018-07-13 | 26 | 0 | 0% | WSM | Jerry Bott | Const 3/6/18 - 10/25/21 | Const in progress
37 | 92 | CHTR | EINSTEIN CHARTERS @ BROOKLYN ES | 2 | 2017-04-14 | 37 | 36 | 97.3% | WSM | Dion Harrington | No funding 'tll 2021 | Pending
93 | 93 | ELEM | ENCANTO ES | 3 | 2018-07-13 | 43 | 43 | 100% | WSM | German Rearte | Completed | Completed
95 | 95 | ELEM | EUCLID ES | 3 | 2018-07-13 | 45 | 45 | 100% | n/a | Richard Kessler | Completed | Completed
103 | 103 | ELEM | FIELD ES | 2 | 2018-07-12 | 23 | 0 | 0% | HVAC-P2 | David Beltran | Const 7/27/17 - 11/26/18 | Const in progress
105 | 105 | ELEM | FLETCHER ES | 2 | 2018-07-12 | 18 | 0 | 0% | HVAC-P2 | Rich Kessler | Const 4/24/17 - 10/25/18 | Const in progress
107 | 107 | ELEM | FLORENCE ES | 2 | 2017-03-29 | 18 | 3 | 16.67% | HVAC-P2 | Rich Kessler | Const 10/20/17 - 3/13/19 | Const in progress
111 | 111 | ELEM | FOSTER ES | 3 | 2018-07-13 | 27 | 27 | 100% | HVAC 2000 | Radik Musin | Completed | Completed
113 | 113 | ELEM | FRANKLIN ES | 3 | 2018-07-13 | 22 | 22 | 100% | HVAC 2000 | Radik Musin | Completed | Completed
115 | 115 | ELEM | FREESE ES | 3 | 2018-07-13 | 28 | 28 | 100% | HVAC 2000 | Michael Appanaitis | Completed | Completed
119 | 119 | ELEM | FULTON ES | 3 | 2018-07-13 | 36 | 36 | 100% | HVAC 2000 | Michael Appanaitis | Completed | Completed
121 | 121 | ELEM | GAGE ES | 3 | 2018-07-13 | 32 | 32 | 100% | HVAC 2000 | Radik Musin | Completed | Completed
123 | 123 | ELEM | BETHUNE ES | 3 | 2018-07-13 | 38 | 38 | 100% | HVAC 2000 | Michael Appanaitis | Completed | Completed
124 | 124 | ELEM | GARFIELD ES | 2 | 2018-07-13 | 35 | 35 | 100% | HVAC-P2 | Rich Kessler | Completed | Completed
125 | 125 | ELEM | ZAMORANO ES | 3 | 2018-07-13 | 65 | 65 | 100% | HVAC 2000 | Michael Appanaitis | Completed | Completed
127 | 127 | ELEM | GRANT ES | 2 | 2018-07-13 | 35 | 33 | 94.29% | WSM | Janet Cortez | 2 CR subject for demolition | Completed
128 | 128 | ELEM | GOLDEN HILL | 2 | 2018-07-13 | 32 | 32 | 100% | HVAC-P2 | Michael Appanaitis | Completed | Completed
130 | 130 | ELEM | JOYNER ES | 3 | 2018-07-13 | 32 | 32 | 100% | n/a | n/a | Completed | Completed
131 | 131 | ELEM | GREEN ES | 3 | 2018-07-13 | 20 | 20 | 100% | n/a | n/a | Completed | Completed
134 | 134 | ELEM | HAGE ES | 2 | 2018-07-13 | 40 | 40 | 100% | HVAC 2000 | Kenneth Shroyer | Completed | Completed
135 | 135 | ELEM | HAMILTON ES | 3 | 2018-07-13 | 37 | 37 | 100% | HVAC 2000 | Kenneth Shroyer | Completed | Completed
136 | 136 | ELEM | HANCOCK ES | 3 | 2018-07-13 | 31 | 31 | 100% | HVAC 2000 / WSM | Jerry Bott; Joel Hermosillo | 3 to be demolished summer 2018 | Completed
137 | 137 | ELEM | RODRIGUEZ ES | 2 | 2018-07-13 | 32 | 32 | 100% | HVAC-P2 | Michael Appanaitis | Completed | Completed
139 | 139 | ELEM | HARDY ES | 3 | 2018-07-13 | 19 | 19 | 100% | n/a | n/a | Completed | Completed
141 | 141 | ELEM | HAWTHORNE ES | 2 | 2018-07-12 | 24 | 0 | 0% | HVAC-P2 | David Beltran | Const 4/5/17 - 10/22/18 | Const in progress
143 | 143 | ELEM | HEARST ES | 3 | 2018-07-13 | 20 | 20 | 100% | HVAC 2000 | Radik Musin | Completed | Completed
107 | 839 | CDC | FLORENCE CDC | 2 | 2015-08-30 | 0 | 0 | 0% | n/a | n/a
289 | 144 | CHTR | HOLLY DRIVE CHARTER @ WEBSTER | 3 | 2018-07-13 | 10 | 10 | 100% | n/a | Richard Kessler | Completed | Completed
147 | 147 | ELEM | HOLMES ES | 2 | 2018-07-13 | 25 | 25 | 100% | HVAC 2000 / ESS | Radik Musin | Completed | Completed
149 | 149 | ELEM | HORTON ES | 3 | 2018-07-13 | 34 | 34 | 100% | HVAC 2000 | Richard Kessler | Completed | Completed
150 | 150 | ELEM | IBARRA ES | 3 | 2018-07-13 | 32 | 32 | 100% | n/a | n/a | Completed | Completed
132 | 153 | ELEM | FAY ES | 3 | 2018-07-13 | 32 | 32 | 100% | n/a | n/a | Completed | Completed
155 | 155 | ELEM | JEFFERSON ES | 2 | 2018-07-13 | 24 | 0 | 0% | HVAC-P2 | Michael Appanaitis | Const 4/29/19 - 8/26/20 | Waiting const start date
156 | 156 | ELEM | JERABEK ES | 3 | 2018-07-13 | 41 | 41 | 100% | n/a | n/a | Completed | Completed
157 | 157 | ELEM | JOHNSON ES | 3 | 2018-07-12 | 30 | 29 | 96.67% | HVAC 2000 | Richard Kessler | 1 CR used as storage/bookrm | Completed
159 | 159 | ELEM | JONES ES | 2 | 2018-07-13 | 23 | 23 | 100% | HVAC-P2 | Joel Early | Completed | Completed
315 | 160 | CHTR | KING/CHAVEZ CHARTER @ MEMORIAL | 2 | 2017-03-29 | 24 | 18 | 75% | WSM | Ray Rodriguez | Const 5/22/19 - 2/11/21 | Waiting const start date
161 | 161 | ELEM | JUAREZ ES | 2 | 2018-07-13 | 19 | 19 | 100% | HVAC-P2 | Joel Early | Completed | Completed
162 | 162 | ELEM | KIMBROUGH ES | 2 | 2018-07-13 | 43 | 3 | 6.977% | HVAC-P2 | Michael Appanaitis | Const 3/25/19 - 9/21/20 | Not in construction per PM 5/7/18
166 | 166 | ELEM | KUMEYAAY ES | 3 | 2018-07-13 | 28 | 28 | 100% | HVAC 2000 | Kenneth Shroyer | Completed | Completed
167 | 167 | ELEM | LAFAYETTE ES | 2 | 2018-07-12 | 32 | 0 | 0% | HVAC-P2 | David Beltran | No const schedule | Waiting const start date
169 | 169 | ELEM | LA JOLLA ES | 1 | 2018-07-12 | 27 | 1 | 3.704% | HVAC-P2 | David Beltran | Const 7/11/17 -10/15/19 | Const in progress
170 | 170 | ATYP/ALTR | LANGUAGE ACADEMY | 3 | 2018-07-13 | 42 | 42 | 100% | n/a | n/a | Completed | Completed
171 | 171 | ELEM | PACIFIC VIEW LEADERSHIP ES | 3 | 2018-07-13 | 26 | 26 | 100% | HVAC 2000 | Michael Appanaitis | Completed | Completed
141 | 842 | CDC | HAWTHORNE CDC | 2 | 2015-08-30 | 0 | 0 | 0% | n/a | n/a
205 | 172 | CHTR | AMERICA'S FINEST CHARTER @ MEAD | 2 | 2018-07-13 | 19 | 4 | 21.05% | HVAC-P2 | Michael Appanaitis | Const 3/14/19 - 9/10/19 | Waiting const start date
173 | 173 | ELEM | LINDA VISTA ES | 2 | 2018-04-19 | 35 | 3 | 8.571% | HVAC-P2 | Richard Kessler | Const 6/15/18 - 2/13/19 | Waiting const start date
175 | 175 | ELEM | LINDBERGH/SCHWEITZER ES | 2 | 2018-07-13 | 47 | 0 | 0% | HVAC-P2 | Joel Early | Const 8/21/17 - 4/3/19 | Const in progress
177 | 177 | ELEM | LOGAN ES | 2 | 2018-07-13 | 29 | 29 | 100% | WSM | Jerry Bott | Completed | Completed
179 | 179 | ELEM | LOMA PORTAL ES | 1 | 2018-07-13 | 19 | 19 | 100% | n/a | n/a | Completed | Completed
181 | 181 | ATYP/ALTR | LONGFELLOW ES | 2 | 2018-07-13 | 35 | 35 | 100% | WSM | Dana Peterson | Completed | Completed
185 | 185 | ELEM | PERKINS ES | 2 | 2018-07-13 | 30 | 7 | 23.33% | HVAC-P2 | Michael Appanaitis | Const 5/3/19 - 7/3/20 | Waiting const start date
195 | 195 | ELEM | MARSHALL ES | 3 | 2018-07-13 | 43 | 43 | 100% | HVAC 2000 | Kenneth Shroyer | Completed | Completed
197 | 197 | ELEM | MARVIN ES | 3 | 2018-07-13 | 25 | 25 | 100% | n/a | n/a | Completed | Completed
199 | 199 | ELEM | MASON ES | 2 | 2018-07-13 | 34 | 34 | 100% | HVAC 2000 | Kenneth Shroyer | Completed | Completed
200 | 200 | ELEM | SALK ES | 2 | 2018-07-13 | 32 | 32 | 100% | n/a | n/a | Completed | Completed
201 | 201 | ELEM | HICKMAN ES | 2 | 2018-07-13 | 33 | 33 | 100% | HVAC 2000 | Kenneth Shroyer | Completed | Completed
203 | 203 | ELEM | MCKINLEY ES | 2 | 2018-07-13 | 28 | 18 | 64.29% | HVAC-P2 | Michael Appanaitis | Const 11/29/17 - 8/23/18 | Const in progress
206 | 206 | ELEM | MILLER ES | 3 | 2018-07-13 | 42 | 35 | 83.33% | HVAC 2000 | Jerry Bott / Mike Clark | 7 Port to be demoed | Completed
210 | 210 | ELEM | MIRAMAR RANCH ES | 3 | 2018-07-13 | 39 | 39 | 100% | HVAC 2000 | Kenneth Shroyer | Completed | Completed
214 | 214 | CHTR | TUBMAN CHARTER | 3 | 2018-07-13 | 14 | 14 | 100% | HVAC 2000 / ESS | Michael Appanaitis | In progress | Const in progress
215 | 215 | ELEM | NORMAL HEIGHTS ES | 2 | 2018-07-13 | 28 | 28 | 100% | n/a | n/a | Completed | Completed
217 | 217 | ELEM | ERICSON ES | 2 | 2018-07-13 | 43 | 43 | 100% | n/a | n/a | Completed | Completed
218 | 218 | ELEM | NYE ES | 3 | 2018-07-13 | 31 | 31 | 100% | HVAC 2000 | Richard Kessler | Completed | Completed
219 | 219 | ELEM | SANDBURG ES | 2 | 2018-07-13 | 35 | 35 | 100% | HVAC 2000 | Kenneth Shroyer | Completed | Completed
329 | 222 | CHTR | ARROYO PASEO CHARTER @ WILSON MS | 2 | 2018-07-13 | 0 | 0 | 0% | WSM | Francisco Campuzano | Demolished port bldgs | Completed
223 | 223 | ELEM | OAK PARK ES | 3 | 2018-07-10 | 44 | 43 | 97.73% | HVAC 2000 | Richard Kessler | 1 CR used as storage/bookrm | Completed
225 | 225 | ELEM | OCEAN BEACH ES | 1 | 2018-07-12 | 22 | 1 | 4.545% | HVAC-P2 | Richard Kessler | Const 12/18/17 - 4/4/19 | Const in progress
227 | 227 | ELEM | PACIFIC BEACH ES | 1 | 2018-07-13 | 18 | 2 | 11.11% | HVAC-P2 | Kenneth Shroyer | Const TBD | Waiting const start date
229 | 229 | ELEM | PARADISE HILLS ES | 3 | 2018-07-13 | 28 | 28 | 100% | HVAC 2000 | Richard Kessler | 4 CR to be demoed | Completed
230 | 230 | ELEM | ROSA PARKS ES | 3 | 2018-07-13 | 56 | 56 | 100% | HVAC 2000 | Kenneth Shroyer | Completed | Completed
235 | 235 | ELEM | PENN ES | 3 | 2018-07-13 | 26 | 26 | 100% | HVAC 2000 | Michael Appanaitis | 3 Port CR NIC (B08, B09, B10)…..5/2/18 | Completed
236N | 236 | ELEM | PORTER NORTH ES | 3 | 2018-07-13 | 26 | 26 | 100% | n/a | n/a | Completed | Completed
236S | 236 | ELEM | PORTER SOUTH ES | 3 | 2018-07-13 | 26 | 26 | 100% | n/a | n/a | Completed | Completed
237 | 237 | ELEM | PERRY ES | 3 | 2018-07-13 | 23 | 23 | 100% | HVAC 2000 | Richard Kessler | Completed | 2 are not CR
243 | 243 | ELEM | ROLANDO PARK ES | 3 | 2018-07-13 | 21 | 21 | 100% | HVAC 2000 | Kenneth Shroyer | Completed | Completed
247 | 247 | ELEM | ROSS ES | 2 | 2018-07-13 | 22 | 22 | 100% | HVAC-P2 | Joel Early | Const 4/14/17 - 7/15/18 | Completed
249 | 249 | ELEM | ROWAN ES | 2 | 2018-07-13 | 21 | 0 | 0% | HVAC-P2 | Michael Appanaitis | Const 7/30/18 - 8/27/19 | Waiting const start date
253 | 253 | ELEM | SEQUOIA ES | 2 | 2018-07-12 | 21 | 0 | 0% | HVAC-P2 | David Beltran | Const 1/9/18 - 9/18/19 | Const in progress
255 | 255 | ELEM | SESSIONS ES | 1 | 2018-07-12 | 25 | 1 | 4% | HVAC-P2 | David Beltran | Const TBD | Waiting const start date
19 | 256 | CHTR | SD COOP CHARTER @ LINDA VISTA ANNEX | 2 | 2017-03-29 | 15 | 0 | 0% | WSM | Ray Rodriguez | Const 1/15/19 - 12/3/20 | Waiting const start date
259 | 259 | ELEM | SHERMAN ES | 2 | 2018-07-13 | 32 | 32 | 100% | HVAC-P2 | Michael Appanaitis | Completed | Completed
261 | 261 | ELEM | SILVERGATE ES | 1 | 2017-03-29 | 27 | 0 | 0% | HVAC-P2 | Richard Kessler | Const 10/6/17 - 4/17/19 | Const in progress
263 | 263 | ELEM | SPRECKELS ES | 2 | 2018-07-13 | 35 | 35 | 100% | HVAC 2000 | 7-HVAC2000, Kenneth Shroyer | Completed | Completed
267 | 267 | CHTR | KING/CHAVEZ CHARTERS @ KING | 2 | 2017-03-29 | 38 | 33 | 86.84% | n/a | Ray Rodriguez | Const 5/1/19 - 1/21/21 | Waiting const start date
269 | 269 | ELEM | SUNSET VIEW ES | 1 | 2018-07-12 | 23 | 2 | 8.696% | HVAC-P2 | Richard Kessler | Const 11/15/18 - 4/15/19 | Waiting const start date
852 | 852 | CDC | LOS ALTOS CDC | 1 | 2015-08-30 | 0 | 0 | 0% | n/a | n/a
274 | 274 | ELEM | TIERRASANTA ES | 3 | 2018-07-13 | 28 | 28 | 100% | HVAC 2000 | 9-HVAC2000, Kenneth Shroyer | Completed | Completed
277 | 277 | ELEM | TOLER ES | 1 | 2018-07-13 | 17 | 0 | 0% | HVAC-P2 | Joel Early | Const 10/26/17 - 9/25/18 | Const in progress
279 | 279 | ELEM | TORREY PINES ES | 1 | 2018-07-13 | 22 | 2 | 9.091% | HVAC-P2 | Kenneth Shroyer | Const 10/13/17 - 2/25/29 | Const in progress
283 | 283 | ELEM | VALENCIA PARK ES | 3 | 2018-07-12 | 42 | 41 | 97.62% | HVAC 2000 | Richard Kessler | 1 CR used as stor unit | Completed
284 | 284 | ELEM | VISTA GRANDE ES | 3 | 2018-07-13 | 26 | 26 | 100% | HVAC 2000 | Kenneth Shroyer | Completed | Completed
285 | 285 | ELEM | WALKER ES | 2 | 2017-03-29 | 33 | 33 | 100% | HVAC-P2 | David Beltran | Completed | Completed
287 | 287 | ELEM | WASHINGTON ES | 2 | 2018-07-13 | 20 | 20 | 100% | HVAC-P2 | Michael Appanaitis | Completed | Completed
289 | 289 | ELEM | WEBSTER ES | 3 | 2018-07-13 | 30 | 30 | 100% | HVAC 2000 / ESS | HVAC2000, HVAC-ESS, Richard Kessler | Completed | Completed
291 | 291 | ELEM | WEGEFORTH ES | 2 | 2018-07-13 | 18 | 1 | 5.556% | HVAC-P2 | Joel Early | Const 9/19/17 - 8/6/18 | Const in progress
293 | 293 | ELEM | BENCHLEY/WEINBERGER ES | 3 | 2018-07-13 | 25 | 25 | 100% | HVAC 2000 / ESS | Michael Appanaitis | Completed | Completed
295 | 295 | ELEM | WHITMAN ES | 2 | 2018-07-12 | 25 | 3 | 12% | HVAC-P2 | David Beltran | Const 6/13/17 - 8/22/18 | Const in progress
165 | 296 | MIDD | KNOX MS | 3 | 2018-07-13 | 33 | 33 | 100% | WSM | Lisa Barnes | Completed | Completed
302 | 302 | MIDD | BELL MS | 3 | 2018-07-13 | 61 | 59 | 96.72% | WSM | Francisco Campuzano | other used as Conf and Student Store | Completed
303 | 303 | MIDD | CHALLENGER MS | 2 | 2018-07-13 | 50 | 7 | 14% | HVAC-P2 | Kenneth Shroyer | Const 8/15/17 - 2/5/20 | Const in progress
304 | 304 | MIDD | CORREIA MS | 1 | 2018-07-12 | 42 | 35 | 83.33% | HVAC-P2 | Richard Kessler | Const 10/18/18 - 4/23/19 | Const in progress | 6 Ports to be demoed S'18
370 | 308 | MIDD | MARSHALL MS | 3 | 2018-07-13 | 60 | 60 | 100% | WSM |  | Completed | Completed
307 | 310 | ATYP/ALTR | CREATIVE PERFORMING & MEIA ARTS @ KROC | 2 | 2018-07-13 | 55 | 55 | 100% | HVAC - WSM | Lisa Barnes | Completed | Completed
311 | 311 | MIDD | LEWIS MS | 3 | 2018-07-13 | 45 | 45 | 100% | HVAC 2000 / ESS | Joel Early | Const 5/30/17 - 1/10/18 | Completed
312 | 312 | MIDD | MANN MS | 3 | 2018-07-13 | 52 | 52 | 100% | HVAC 2000 | Richard Kessler | Completed | Completed
313 | 313 | MIDD | MARSTON MS | 2 | 2018-07-13 | 48 | 1 | 2.083% | HVAC-P2 | Joel Early | Const 2/9/18 - 4/10/19 | Const in progress
316 | 316 | MIDD | MONTGOMERY MS | 2 | 2018-07-13 | 43 | 0 | 0% | WSM | Dana Peterson | Const 9/10/19 - 9/22/20 | Waiting const start date
317 | 317 | MIDD | MUIRLANDS MS | 1 | 2018-07-13 | 41 | 0 | 0% | HVAC-P2 | Kenneth Shroyer | Const 8/23/18 - 2/10/20 | Const in progress
319 | 319 | CHTR | O'FARRELL CHARTER | 3 | 2018-07-13 | 61 | 61 | 100% | WSM | Steve Faust | Completed | Completed
320 | 320 | MIDD | PACIFIC BEACH MS | 1 | 2018-07-13 | 42 | 0 | 0% | WSM | German Rearte | Const 1/14/19 - 7/14/20 | Waiting const start date
225 | 894 | CDC | OCEAN BEACH CDC | 1 | 2018-07-12 | 0 | 0 | 0% | n/a | n/a
321 | 321 | MIDD | PERSHING MS | 3 | 2018-07-13 | 38 | 38 | 100% | WSM | Alonso Casas | Completed | Completed
322 | 322 | MIDD | CLARK MS | 3 | 2018-07-13 | 58 | 58 | 100% | WSM | Tom Hart | Const 5/3/16 - 8/16/18 | Completed
324 | 324 | MIDD | ROOSEVELT MS | 2 | 2018-07-13 | 58 | 24 | 41.38% | HVAC-P2 | Michael Appanaitis | Const 4/15/19 - 6/15/20 | Waiting const start date
325 | 325 | MIDD | STANDLEY MS | 2 | 2018-07-12 | 46 | 44 | 95.65% | HVAC-P2 | David Beltran | Const 4/26/17 - 8/23/17 | Project Completed
326 | 326 | MIDD | TAFT MS | 2 | 2018-07-13 | 33 | 33 | 100% | WSM | Alonso Casas | Completed | Completed
327 | 327 | MIDD | DE PORTOLA MS | 3 | 2018-07-13 | 40 | 40 | 100% | HVAC 2000 | Kenneth Shroyer | Completed | Completed
328 | 328 | MIDD | WANGENHEIM MS | 2 | 2018-07-12 | 55 | 34 | 61.82% | HVAC-P2 | David Beltran | Const 3/3/17 - 10/22/18 | Const in progress
329 | 329 | MIDD | WILSON MS | 2 | 2018-07-13 | 66 | 1 | 1.515% | WSM | Francisco Campuzano | Const 7/16/18 - 5/20/20 | Waiting const start date
315 | 330 | MIDD | MEMORIAL PREPARATORY | 2 | 2017-03-30 | 45 | 23 | 51.11% | WSM | Jerry Bott | Const 10/31/17 - 11/13/19 | Const in progress
208 | 331 | ATYP/ALTR | ALBA SCHOOL | 2 | 2018-07-13 | 12 | 12 | 100% | n/a | n/a | Completed | Completed
332 | 332 | HIGH | CLAIREMONT HS | 1 | 2018-05-07 | 77 | 7 | 9.091% | HVAC-P2 | Joel Early / Bryan Ehm | Const 2/9/18 - 2/14/19 | Const in progress
334 | 334 | HIGH | CRAWFORD HS | 3 | 2017-04-05 | 69 | 67 | 97.1% | HVAC 2000 | Richard Kessler | 2- No A/C schedule | Completed
338 | 338 | HIGH | HOOVER HS | 3 | 2018-07-09 | 100 | 94 | 94% | HVAC 2000 | Richard Kessler | Const 4/3/17 - 11/1/18 | Const in progress
336 | 336 | HIGH | HENRY HS | 3 | 2018-07-13 | 97 | 96 | 98.97% | WSM | Julio Ramos | Completed; New bldg in process | Completed
335E | 341 | ATYP/ALTR | MILLENNIAL TECH @ GOMPERS EAST | 3 | 2018-07-13 | 30 | 30 | 100% | HVAC 2000 | Richard Kessler | Completed | Completed
342 | 342 | HIGH | LA JOLLA HS | 1 | 2018-07-13 | 58 | 19 | 32.76% | WSM | Alonso Casas | Const 2/7/19 - 9/8/20 | Waiting const start date
188 | 343 | MIDD | INNOVATION MS @ MACDOWELL | 2 | 2018-07-13 | 40 | 40 | 100% | WSM | Mark Lawrence | 5 port to be demoed 8/1/18 | Completed
344 | 344 | HIGH | LINCOLN HS | 3 | 2018-07-13 | 114 | 114 | 100% | n/a | Michael Appanaitis | Completed | Completed
346 | 346 | HIGH | MADISON HS | 2 | 2018-07-12 | 80 | 6 | 7.5% | HVAC-P2 | David Beltran | Const 1/9/18 - 5/28/19 | Const in progress
249 | 856 | CDC | ROWAN CDC | 2 | 2018-05-07 | 0 | 0 | 0% | n/a | n/a
349 | 349 | HIGH | MIRA MESA HS | 2 | 2018-07-13 | 110 | 110 | 100% | HVAC 2000 | Kenneth Shroyer | Completed | Completed
350 | 350 | HIGH | MISSION BAY HS | 1 | 2017-03-30 | 77 | 18 | 23.38% | WSM | WSM, Janet Cortez | Const 5/23/18 -7/29/19 | Const in progress
352 | 352 | HIGH | MORSE HS | 3 | 2018-07-13 | 98 | 98 | 100% | HVAC 2000 | Michael Appanaitis | Completed | Completed
354 | 354 | HIGH | POINT LOMA HS | 1 | 2018-07-13 | 89 | 87 | 97.75% | WSM | Annalyn Roxas | 2 CR not to have AC | Completed
355 | 355 | HIGH | UNIVERSITY CITY HS | 2 | 2018-07-13 | 79 | 58 | 73.42% | HVAC 2000-WSM | Alonso Casas | Const 12/13/17 - 8/23/19 | Const in progress
357 | 357 | HIGH | SERRA HS | 3 | 2018-07-13 | 89 | 86 | 96.63% | HVAC 2000 | Jerry Bott | 3 rooms NIC | Completed
359 | 359 | HIGH | SCRIPPS RANCH HS | 3 | 2018-07-12 | 102 | 97 | 95.1% | HVAC 2000 | Kenneth Shroyer | (5 rms) Heat and vent only. | Completed
361 | 361 | ATYP/ALTR | GARFIELD HS | 2 | 2018-07-13 | 26 | 26 | 100% | HVAC-P2 | Michael Appanaitis | Completed | Completed
364 | 364 | ATYP/ALTR | RILEY SCHOOL | 2 | 2018-07-13 | 17 | 17 | 100% | WSM | Dana Peterson | Completed | Completed
365 | 365 | CHTR | KEILLER CHARTER | 3 | 2018-07-13 | 31 | 31 | 100% | HVAC 2000 | Michael Appanaitis | B12,B22 = Not CR; No AC | Completed
367 | 367 | MIDD | FARB MS | 3 | 2018-07-13 | 38 | 38 | 100% | n/a | n/a | Completed | Completed
368 | 368 | ATYP/ALTR | SCHOOL OF CREATIVE AND PERF ARTS | 3 | 2018-07-13 | 66 | 66 | 100% | HVAC 2000 | Michael Appanaitis | Completed | Completed
5 | 369 | ATYP/ALTR | MUIR SCHOOL | 2 | 2018-07-13 | 19 | 19 | 100% | HVAC-P2 | Joel Early | Const 5/19/17 - 5/20/18 | Completed
90 | 377 | CHTR | INNOVATIONS CHARTER @ SPRING CANYON | 3 | 2018-07-13 | 20 | 20 | 100% | n/a | n/a | Completed | Completed
299 | 395 | ATYP/ALTR | MT. EVEREST ACADEMY @ WIGGIN | 2 | 2018-07-13 | 17 | 4 | 23.53% | HVAC-P2 | Joel Early | Const 9/18/17 - 02/22/19 | Const in progress
364 | 438 | ATYP/ALTR | NEW DAWN @ RILEY | 2 | 2018-07-13 | 5 | 5 | 100% | WSM | Dana Peterson | Const 5/31/16 - 9/1/17 | Completed
297 | 439 | ATYP/ALTR | WHITTIER | 2 | 2018-07-13 | 28 | 6 | 21.43% | HVAC-P2 | Joel Early | Const 12/ 5/17 - 11/30/18 | Const in progress
117 | 504 | OCP | I HIGH VIRTUAL ACADEMY @ FREMONT | 2 | 2018-07-13 | 7 | 7 | 100% | HVAC-P2 |  | Completed | Completed
335W | 747 | CHTR | GOMPERS CHARTER @ GOMPERS WEST | 3 | 2018-07-12 | 66 | 25 | 37.88% | HVAC 2000 | Richard Kessler | Const9/5/17 - 10/1/18 | Const in progress
3 | 789 | CHTR | SD GLOBAL VISION CHARTER @ ADAMS | 2 | 2018-07-13 | 11 | 11 | 100% | WSM | Dana Peterson | Completed | Completed
15 | 795 | CHTR | SD COOP CHARTER @ BANDINI | 2 | 2018-07-13 | 8 | 0 | 0% | WSM | Jerry Bott | Const 8/24/18 - 5/1/19 | Waiting const start date
91 | 795 | CHTR | SD COOP CHARTER @ EMERSON | 2 | 2018-07-13 | 8 | 0 | 0% | WSM | Jerry Bott | Const 3/7/18 - 12/3/19 | Const in progress
75 | 796 | CHTR | KAVOD CHARTER @ CUBBERLY | 2 | 2018-07-13 | 9 | 9 | 100% | HVAC-P2 | Joel Early | Const 7/12/17 - 2/9/18 | Completed
834 | 834 | CDC | BAYVIEW CDC | 1 | 2018-07-13 | 3 | 3 | 100% | n/a | n/a | Completed | Completed
835 | 835 | CDC | BROOKLYN CDC | 2 | 2018-07-13 | 3 | 3 | 100% | HVAC-P2 | Michael Appanaitis | Completed | Completed
85 | 836 | CDC | DEWEY CDC | 1 | 2017-03-30 | 5 | 0 | 0% | n/a | n/a
838 | 838 | CDC | EUCLID CDC | 3 | 2018-07-13 | 5 | 5 | 100% | n/a | n/a | Completed | Completed
124 | 840 | CDC | GARFIELD CDC | 2 | 2018-07-13 | 4 | 4 | 100% | n/a | n/a | CR Count is 0..4-CDC | Completed
846 | 846 | CDC | KENNEDY CDC | 3 | 2018-07-13 | 3 | 3 | 100% | n/a | n/a | CR Count is 0…3-CDC | Completed
177 | 850 | CDC | LOGAN CDC | 2 | 2018-07-13 | 4 | 4 | 100% | WSM | Jerry Bott | CR Count is 0…3-CDC & 1-ERL | Completed
170 | 854 | CDC | MONTEZUMA CDC @ LANGUAGE ACAD | 3 | 2018-07-13 | 3 | 3 | 100% | n/a | n/a | CR Count is 0…3-CDC | Completed
219 | 857 | CDC | SANDBURG CDC | 2 | 2018-07-13 | 2 | 2 | 100% | HVAC 2000 | Kenneth Shroyer | CR Count is 0…2-CDC | Completed
287 | 858 | CDC | SALOMON CDC @ WASHINGTON | 2 | 2018-07-13 | 4 | 4 | 100% | n/a | n/a | Completed | Completed
285 | 859 | CDC | WALKER CDC | 2 | 2018-07-13 | 4 | 4 | 100% | n/a | n/a | Completed | Completed
291 | 860 | CDC | WEGEFORTH CDC | 2 | 2018-07-13 | 2 | 2 | 100% | n/a | n/a | Completed | Completed
105 | 883 | CDC | FLETCHER CDC | 2 | 2018-07-13 | 2 | 2 | 100% | n/a | n/a | Completed | Completed
247 | 896 | CDC | ROSS CDC | 2 | 2018-07-13 | 2 | 2 | 100% | HVAC-P2 | Joel Early | Const 4/14/17 - 7/15/18 | Completed
340 | 3732 | HIGH | KEARNY HS COMPLEX | 2 | 2018-07-13 | 71 | 11 | 15.49% | HVAC-P2 | Joel Early | Const 4/16/18 - 12/7/18 | Const in progress
356 | 3749 | HIGH | SAN DIEGO HS COMPLEX | 2 | 2018-07-13 | 119 | 88 | 73.95% | WSM | Lisa Barnes | Const 8/7/18 - 1/29/20 | Const in progress
362 | 0362A | ATYP/ALTR | TWAIN MAIN @ LINDA VISTA RD | 2 | 2018-04-19 | 26 | 6 | 23.08% | HVAC-P2 | Richard Kessler | Const 9/5/17 - 12/7/18 | Const in progress
349 | 0362C | ATYP/ALTR | TWAIN MESA @ MIRA MESA | 2 | 2018-07-13 | 5 | 5 | 100% | HVAC 2000 | Kenneth Shroyer | Completed | Completed
352 | 0362E | ATYP/ALTR | TWAIN MORSE | 3 | 2018-07-13 | 11 | 11 | 100% | HVAC 2000 | Michael Appanaitis | B01, B08 = Not CR; No AC; Completed 7/9/18 | Completed
|  |  | TOTALS |  |  | 6867 | 5048 | 73.51%